## HR
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Send the three gap-closing messages (IT, Security, Operations leadership) | 2026-09-29 | HR | Y | Not started | Not started | Not started | Start minus 4 business days. Source: (suggested, not policy). Drafts are in section 8 of the plan.
Confirm day-1 start time and each hire's time zone | 2026-09-29 | HR | Y | Not started | Not started | Not started | Start minus 4 business days. Source: (suggested, not policy). [HR to confirm #7: day-1 start time and standard hours] [HR to confirm #8: hire time zones]
Send pre-start paperwork: I-9 process and state new-hire forms | 2026-09-30 | HR | Y | Not started | Not started | Not started | Start minus 3 business days. Source: (suggested, not policy). [HR to confirm #4: I-9 process and timing] [HR to confirm #5: state new-hire forms]
Send HR onboarding calendar invite for day 1 | 2026-09-30 | HR | N | Not started | Not started | Not started | Start minus 3 business days. Source: (suggested, not policy). 11:30 AM-12:30 PM ET
Create ADP profiles (payroll, time off) | 2026-10-01 | HR | N | Not started | Not started | Not started | Start minus 2 business days. Source: Systems list (SAMPLE). [HR to confirm #6: payroll and benefits setup]
Prepare handbook and acknowledgment for day 1 | 2026-10-01 | HR | N | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy). [HR to confirm #2: employee handbook]
Confirm required-training list and the confidentiality/PII course | 2026-10-01 | HR | Y | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy). [HR to confirm #3: required-training list]
Confirm confidentiality agreement process | 2026-10-01 | HR | N | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy). [HR to confirm #12: confidentiality agreement]
Confirm each hire's background check has cleared | 2026-10-02 | HR | Y | Not started | Not started | Not started | Start minus 1 business day. Source: ISP-01 §7. Confirm status today. Policy requires completion before the start date. [HR to confirm #1: background check status]
Run day-1 HR onboarding session | 2026-10-05 | HR | N | Not started | Not started | Not started | Start date. Source: (suggested, not policy).
Schedule 30-day HR check-in with each hire | 2026-10-09 | HR | N | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy). Held on or near Wed Nov 4

## Hiring manager
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Name the interim manager for the cohort | 2026-09-29 | Hiring manager | Y | Not started | Not started | Not started | Start minus 4 business days. Source: (suggested, not policy). [Intake Team Lead - vacant]. [HR to confirm #13: interim manager]
Approve access requests (M365, Ecosystem Intake, ADP, KnowBe4) | 2026-09-30 | Hiring manager | Y | Not started | Not started | Not started | Start minus 3 business days. Source: ISP-02 §2. Least privilege, manager approval. [HR to confirm #14: access approver]
Name the trainer and a buddy for each hire | 2026-09-30 | Hiring manager | Y | Not started | Not started | Not started | Start minus 3 business days. Source: (suggested, not policy). [HR to confirm #15: trainer and buddies]
Send welcome email to each hire | 2026-09-30 | Hiring manager | N | Not started | Not started | Not started | Start minus 3 business days. Source: (suggested, not policy). Drafts in section 9. Day-1 time in each hire's time zone.
Send week-1 calendar invites (daily huddle, check-ins, training blocks) | 2026-10-01 | Hiring manager | N | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy).
Lead day-1 welcome call and end-of-day check-in | 2026-10-05 | Hiring manager | N | Not started | Not started | Not started | Start date. Source: (suggested, not policy).
Hold a 15-minute 1:1 with each hire | 2026-10-08 | Hiring manager | N | Not started | Not started | Not started | Start plus 3 business days. Source: (suggested, not policy).
Readiness gate review and sign-off per hire | 2026-10-09 | Hiring manager | Y | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy). Section 6
Schedule 30/60/90-day reviews | 2026-10-09 | Hiring manager | N | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy). Nov 4, Dec 4, Jan 4

## Trainer
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Confirm training content: request types, Ecosystem fields, carrier matching, deficiency notices, subpoena/court order priority | 2026-10-01 | Trainer | N | Not started | Not started | Not started | Start minus 2 business days. Source: (inferred from JD). [HR to confirm #16: deficiency notice process] [HR to confirm #17: intake SOP and validity rules] [HR to confirm #18: priority rules for subpoenas and court orders]
Build a practice set of sample or de-identified requests (no live claim data) | 2026-10-02 | Trainer | Y | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy). Depends on [HR to confirm #21: practice environment]
Build answer key and accuracy scoring sheet for the practice set | 2026-10-02 | Trainer | N | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy).
Deliver week-1 training blocks | 2026-10-06 | Trainer | N | Not started | Not started | Not started | Start plus 1 business day. Source: (suggested, not policy). Tue Oct 6 to Fri Oct 9
Score the Friday practice assessment and share with the manager | 2026-10-09 | Trainer | Y | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy). Pass mark [HR to confirm #10: intake volume and accuracy targets]

## IT
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Confirm equipment shipment and tracking; expedite anything not shipped | 2026-09-29 | IT | Y | Not started | Not started | Not started | Start minus 4 business days. Source: (suggested, not policy). Target delivery Thu Oct 1. [HR to confirm #20: equipment shipment]
Confirm the Ecosystem practice/sandbox environment | 2026-09-29 | IT | Y | Not started | Not started | Not started | Start minus 4 business days. Source: (suggested, not policy). [HR to confirm #21: practice environment]
Create individual Microsoft 365 accounts (Outlook, Teams, OneDrive) | 2026-09-30 | IT | Y | Not started | Not started | Not started | Start minus 3 business days. Source: Systems list (SAMPLE). Everyone gets M365; IT grants.
Set up MFA for remote access | 2026-10-01 | IT | Y | Not started | Not started | Not started | Start minus 2 business days. Source: ISP-02 §1. [HR to confirm #23: MFA method]
Create individual Ecosystem Intake accounts, practice access only | 2026-10-02 | IT | Y | Not started | Not started | Not started | Start minus 1 business day. Source: ISP-02 §2, §5; Systems list (SAMPLE). No shared logins. Granted by Intake Team Lead + IT (vacant, see #14).
Send login instructions separately from the welcome email | 2026-10-02 | IT | N | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy).
Confirm day-1 IT support contact | 2026-10-02 | IT | N | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy). [HR to confirm #24: day-1 IT support]
Run day-1 setup and login check | 2026-10-05 | IT | Y | Not started | Not started | Not started | Start date. Source: (suggested, not policy). 10:30-11:30 AM ET
Enable live Ecosystem Intake access after the readiness gate is signed | 2026-10-09 | IT | Y | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy). Not before manager sign-off

## Security
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Confirm incident-reporting steps to teach on day 2 | 2026-10-01 | Security | N | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy). [HR to confirm #26: incident reporting]
Enroll hires in security awareness training (KnowBe4) | 2026-10-02 | Security | Y | Not started | Not started | Not started | Start minus 1 business day. Source: ISP-01 §6; Systems list (SAMPLE). [HR to confirm #25: at-hire security training]
Deliver security and data protection session | 2026-10-06 | Security | N | Not started | Not started | Not started | Start plus 1 business day. Source: (suggested, not policy). Tue Oct 6, 2:00-3:00 PM ET
Confirm security training completion for the readiness gate | 2026-10-08 | Security | Y | Not started | Not started | Not started | Start plus 3 business days. Source: ISP-01 §6.
Add hires to quarterly phishing simulations | 2026-10-09 | Security | N | Not started | Not started | Not started | Start plus 4 business days. Source: ISP-01 §6.

## New hire
Item | Due date | Owner | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Notes
Confirm shipping address and that equipment arrived | 2026-10-01 | New hire | Y | Not started | Not started | Not started | Start minus 2 business days. Source: (suggested, not policy).
Complete pre-start HR forms | 2026-10-02 | New hire | Y | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy). [HR to confirm #4: I-9 process and timing] [HR to confirm #5: state new-hire forms]
Set up a private workspace for handling confidential documents | 2026-10-02 | New hire | N | Not started | Not started | Not started | Start minus 1 business day. Source: (suggested, not policy).
Log in, enroll MFA, complete HR onboarding | 2026-10-05 | New hire | Y | Not started | Not started | Not started | Start date. Source: ISP-02 §1.
Complete security awareness training | 2026-10-07 | New hire | Y | Not started | Not started | Not started | Start plus 2 business days. Source: ISP-01 §6.
Complete confidentiality and PII training | 2026-10-08 | New hire | Y | Not started | Not started | Not started | Start plus 3 business days. Source: (suggested, not policy). [HR to confirm #3: required-training list]
Complete the Friday practice assessment | 2026-10-09 | New hire | N | Not started | Not started | Not started | Start plus 4 business days. Source: (suggested, not policy).

## Readiness gate
Condition | Expected date | Confirmed by | Blocking? (Y/N) | Dana Ortiz | Marcus Webb | Priya Nair | Source / notes
Criminal background check completed | 2026-10-02 | HR (Kaela French) | Y | Not started | Not started | Not started | ISP-01 §7 (before start date)
MFA enrolled for remote access | 2026-10-05 | IT | Y | Not started | Not started | Not started | ISP-02 §1
Individual, least-privilege Ecosystem Intake account approved by a manager | 2026-10-02 | Manager + IT | Y | Not started | Not started | Not started | ISP-02 §2, §5
Security awareness training complete | 2026-10-07 | Security & Facilities Manager | Y | Not started | Not started | Not started | ISP-01 §6
Confidentiality and PII training complete | 2026-10-08 | HR | Y | Not started | Not started | Not started | [HR to confirm #3: required-training list]
Practice assessment passed on sample data | 2026-10-09 | [Trainer - TBD] | Y | Not started | Not started | Not started | (suggested, not policy); pass mark [HR to confirm #10: intake volume and accuracy targets]
Manager sign-off | 2026-10-09 | [Intake Team Lead - vacant] / interim | Y | Not started | Not started | Not started | [HR to confirm #13: interim manager]

## Missing info
# | Ask | Question | Blocking? (Y/N) | Answer | Answered by | Notes
1 | HR | Has each hire's criminal background check cleared? ISP-01 §7 requires it before the start date for anyone with access to client data. If one is not clear by Fri Oct 2, does that hire's start date move? | Y
2 | HR | Where is the current employee handbook, and how do new hires acknowledge it? | N
3 | HR | What is the required-training list for new hires, and which course counts as confidentiality and PII training for the readiness gate? | Y
4 | HR | What is ClaimFox's I-9 / employment eligibility process and timing for remote hires? | Y
5 | HR | Which state-specific new-hire forms or notices apply for New York, Florida and Texas? | N
6 | HR | Pay schedule, direct deposit setup and benefits enrollment window to cover in ADP on day 1. | N
7 | HR | What are standard working hours, and what time should day 1 start? (This plan assumes 10:00 AM ET / 9:00 AM CT.) | Y
8 | HR | Confirm each hire's time zone. Marcus (Florida) is ET unless he is in the panhandle (CT). Priya (Texas) is CT unless she is in the El Paso area (MT). | Y
9 | HR | Is there a probation or introductory period for this role, and what does it involve? | N
10 | HR | The JD says associates meet daily intake volume and accuracy targets. What are the numbers, and what is the ramp for a new hire at 30/60/90 days? | N
11 | HR | Is Monday Oct 12 (Columbus Day / Indigenous Peoples' Day) a company holiday? It affects the week-2 start of live work. | N
12 | HR | Do new hires sign a confidentiality agreement or NDA, and when? | N
13 | Manager | Who manages Dana, Marcus and Priya while the Intake Team Lead role is vacant? That person signs the readiness gate, runs check-ins and sends the welcome emails. | Y
14 | Manager | Who approves system access? ISP-02 §2 requires manager approval, and the systems list says Ecosystem Intake is granted by the Intake Team Lead + IT. | Y
15 | Manager | Who trains the cohort in week 1, and which experienced associate is each hire's buddy? | Y
16 | Manager | How are deficiency notices sent (Ecosystem, Outlook, other), and where are the approved templates? | N
17 | Manager | Is there a written intake procedure: what makes each request type complete and valid, and how requests are matched to the carrier client and claim file? | N
18 | Manager | What are the priority-handling and escalation rules for subpoenas and court orders with return dates? | N
19 | Manager | When do new associates move from practice to live requests, and what QA review applies at first? | N
20 | IT | Are laptops (and any other equipment) being shipped to all three hires? Has it shipped, and what is the tracking? | Y
21 | IT | Is there an Ecosystem training/sandbox environment or a de-identified practice data set? Week 1 depends on it. | Y
22 | IT | The systems list in the skill is a SAMPLE. Confirm the systems a Global Intake Associate gets and who grants each. | N
23 | IT | Which MFA method do remote staff use (ISP-02 §1 requires MFA for all remote access), and can it be set up on day 1? | Y
24 | IT | Who is on call for day-1 IT problems, and how do hires reach them if the laptop will not log in? | N
25 | Security | Confirm KnowBe4 is the platform (it comes from the SAMPLE list) and which modules satisfy the at-hire security awareness training in ISP-01 §6. | Y
26 | Security | How does an associate report a suspected incident, such as a record sent to the wrong requestor? ISP-03 covers the response plan but not the employee reporting step. | N
27 | Security | May intake associates use Claude, and may any request data go into it? The AI use policy is still a DRAFT, so this plan does not cite it. | N
28 | Security | ISP-01 §4 says client data is not accessed outside the United States. How should new remote hires be told this applies to travel? | N